## Report
Crew 2 Weekly Backlog Report - (BAS/HVAC/MECH)
WO# | Description |  | Location | Priority | Rep Date |  |  | Status | Status Date |  | Lead | Craft | Work Type |  |  | Est. Duration (WO Tab) | PLH (Planned Labor Hrs) | ALH (Actual Labor Hrs) | Planned-Actual Hrs
261870 | 64-3040/45...Connect MicroVent rack to JCI |  | 64-3040 | 4 | 2018-05-04 13:35 | 43224.566 |  | APPR | 2018-11-09 10:29 | 43413.4371 | WAC | BAS | RM |  |  | 02:00 | 03:00 | 00:00 | 03:00
266134 | Replace Carriage Drive on JMS Rack Washer |  | 28-1050 | 3 | 2018-08-10 13:26 | 43322.56 |  | APPR | 2019-09-17 12:57 | 43725.5397 | BOB | BAS | CM |  |  | 03:00 | 03:00 | 02:00 | 01:00
272482 | RLAB Animal Room Calibration Temp & Humidity 2019 |  | JAXLABS | 4 | 2018-12-10 04:02 | 43444.1681 |  | APPR | 2019-02-20 08:56 | 43516.3723 | NOYESB | BAS | PM |  |  | 100:00 | 120:00 | 108:30 | 11:30
272483 | JMS Animal Room Calibration Temp & Humidity 2019 |  | JAXLABS | 4 | 2018-12-10 04:02 | 43444.1681 |  | APPR | 2019-02-20 08:58 | 43516.3734 | NOYESB | BAS | PM |  |  | 100:00 | 120:00 | 48:30 | 71:30
275292 | [CP] Card Acces Upgrade Planning PEP 19-50 |  | JAXLABS | 4 | 2019-02-08 15:16 | 43504.6365 |  | APPR | 2019-02-08 15:17 | 43504.637 | BOB | BAS | CP |  |  | 04:00 | 200:00 | 299:00 | -99:00
277204 | 74-3002...Humidity Latch not activating at correct point |  | 74-3002 | 3 | 2019-03-11 05:26 | 43535.2266 |  | APPR | 2019-03-11 07:52 | 43535.3278 | WAC | BAS | CM |  |  | 01:00 | 01:00 | 00:00 | 01:00
277545 | [CP] Autoclave Control Upgrades Phs II PEP 19-20 (2019 CAP Proj.) |  | 28-1 | 4 | 2019-03-19 08:51 | 43543.3687 |  | INPRG | 2020-05-04 07:32 | 43955.314 |  | BAS | CP |  |  | 100:00 | 80:00 | 11:00 | 69:00
277548 | [CP] BHB Condensate Sys Upgr, Bldg 50 & 28 (PEP 20-22) |  | 03 | 4 | 2019-03-19 08:58 | 43543.3739 |  | INPRG | 2020-06-17 08:41 | 43999.3621 |  | HVAC&R | CP |  |  | 120:00 | 160:00 | 00:00 | 160:00
277718 | Annual Check of PLC Program Backups |  | JAXLABS | 3 | 2019-03-25 04:01 | 43549.1675 |  | APPR | 2019-09-17 13:04 | 43725.5443 | BOB | BAS | PM |  |  | 08:00 | 12:00 | 00:00 | 12:00
277889 | BHMETASYS01 Audits and maintenance |  | 50-B101A |  | 2019-03-29 08:10 | 43553.3405 |  | INPRG | 2019-03-29 08:13 | 43553.3422 | BOB | BAS | PM |  |  | 16:00 | 00:00 | 07:00 | -07:00
278027 | NRB Freezer Farm....Re-Program & test John Lab So-Low alarm in JCI |  | 33-2150 | 4 | 2019-04-02 07:26 | 43557.3098 |  | APPR | 2019-04-02 07:29 | 43557.3119 |  | BAS | RM |  |  | 01:00 | 00:00 | 00:00 | 00:00
279093 | re-arrange office to make room for new position |  | 50-B101A | 4 | 2019-04-26 08:23 | 43581.349 |  | INPRG | 2019-04-26 08:26 | 43581.3517 |  | BAS | NC |  |  | 08:00 | 00:00 | 32:00 | -32:00
FS0013723 | 01D-offices 2171, 2173, 2175, 2177, and 2183 are reporting high temperatures (~76 degrees) |  | 01D-2 | 4 | 2019-05-13 12:22 | 43598.5155 |  | APPR | 2019-05-13 13:27 | 43598.5603 | BOB | BAS | CM |  |  | 01:00 | 01:00 | 00:00 | 01:00
280427 | B74 reheat valves not opening |  | 74-P | 3 | 2019-05-15 10:44 | 43600.447 |  | APPR | 2019-06-14 14:25 | 43630.6009 | NOYESB | BAS | CM |  |  | 00:00 | 00:00 | 10:00 | -10:00
282166 | Upgrade to JCI 10.0 |  |  | 3 | 2019-06-18 14:54 | 43634.621 |  | INPRG | 2019-06-18 14:55 | 43634.6217 | BOB | BAS | PM |  |  | 00:00 | 00:00 | 22:00 | -22:00
282437 | MGL 375/377 Flow alarms-Rewire alarm circuit to NC |  | 19-3630F | 3 | 2019-06-26 09:22 | 43642.39 |  | APPR | 2020-05-21 13:38 | 43972.5678 | NOYESB | BAS | CM |  |  | 02:00 | 16:00 | 04:00 | 12:00
282609 | 53-G107...Modify BSL2 space air changes |  | 53-G107 | 3 | 2019-07-02 07:41 | 43648.3198 |  | APPR | 2019-07-02 07:43 | 43648.3217 | BOB | BAS | CM |  |  | 00:00 | 02:00 | 00:00 | 02:00
283548 | B74 Air Compressor-Connect air line to main lab system.( order 100 ft hose) |  | 74-G130 | 3 | 2019-07-24 14:08 | 43670.5889 |  | APPR | 2019-11-13 14:56 | 43782.6222 | HWL | HVAC&R | CM |  |  | 08:00 | 08:00 | 34:30 | -26:30
284601 | 01D-3070...HVAC Modification Request (see long description) |  | 01D-3070 | 4 | 2019-08-13 11:29 | 43690.4786 |  | APPR | 2019-08-22 07:12 | 43699.3003 | MCCUER | HVAC&R | RM |  |  | 02:00 | 00:00 | 00:00 | 00:00
284660 | [CP] B62 JAX Warehouse Facility-BAS Support |  | 62 | 4 | 2019-08-16 14:22 | 43693.5984 |  | APPR | 2019-08-16 14:22 | 43693.5985 |  | BAS | CP |  |  | 160:00 | 00:00 | 63:30 | -63:30
285354 | [CP] Snell 2nd Floor Reno Maintenance Support - HVAC&R |  | 21-2 | 4 | 2019-08-29 08:48 | 43706.3669 |  | APPR | 2019-08-29 08:50 | 43706.3682 | MCCUER | HVAC&R | CP |  |  | 24:00 | 06:00 | 03:00 | 03:00
285355 | [CP] Snell 2nd Floor Reno Maintenance Support - MECH |  | 21-2 | 4 | 2019-08-29 08:49 | 43706.3672 |  | APPR | 2019-08-29 08:50 | 43706.3682 | PBARBEAU | MECH | CP |  |  | 24:00 | 16:00 | 02:00 | 14:00
285357 | [CP] Snell 2nd Floor Reno Maintenance Support - BAS |  | 21-2 | 4 | 2019-08-29 08:52 | 43706.3693 |  | APPR | 2019-08-29 08:52 | 43706.3695 | BOB | BAS | CP |  |  | 24:00 | 80:00 | 339:30 | -259:30
286120 | BAS RAF CSA & WASH AREA day/night not working (sensor/switch shorted) |  | 20-1675 | 4 | 2019-09-09 15:15 | 43717.6357 |  | APPR | 2020-06-24 15:19 | 44006.6383 | NOYESB | BAS | CM |  |  | 03:00 | 06:00 | 01:00 | 05:00
286187 | B28/51 check chilled water system . including ahu4-28 |  | 28-2055 | 3 | 2019-09-13 16:19 | 43721.6795 |  | APPR | 2019-09-13 16:20 | 43721.6803 | NOYESB | BAS | CM |  |  | 05:00 | 00:00 | 06:30 | -06:30
286406 | SM...REPLACE HEATPUMP BLD 54 CONTROL ROOM |  | 54-1030 | 3 | 2019-09-21 12:24 | 43729.5169 |  | INPRG | 2019-09-26 11:28 | 43734.4778 | MCCUER | HVAC&R | CM |  |  | 30:00 | 30:00 | 36:00 | -06:00
FS0018318 | 53-G125...Oxygen monitoring system needs evaluation (see long description) |  | 53-G125 | 3 | 2019-09-23 10:04 | 43731.4193 |  | APPR | 2019-09-30 13:12 | 43738.5497 | WAC | BAS | CM |  |  | 02:00 | 00:00 | 02:00 | -02:00
FS0018478 | 54-1000...Support requested with testing SBS-H2 Hydrogen sensor |  | 54-1000 | 4 | 2019-09-27 13:32 | 43735.5637 |  | APPR | 2019-12-10 09:01 | 43809.3754 | WAC | BAS | CM |  |  | 01:00 | 01:00 | 05:00 | -04:00
FS0018987 | 57-2930...Women's locker room in fitness center is warm in the morning. |  | 57-2930 | 4 | 2019-10-16 10:51 | 43754.4523 |  | INPRG | 2019-11-11 14:44 | 43780.6142 | WAC | BAS | RM |  |  | 01:00 | 00:00 | 00:00 | 00:00
287907 | Replace all AHU Door Gaskets - 59-3130D...Leak dripping in office yesterday during heavy rains |  | 59-3130D | 3 | 2019-10-25 13:51 | 43763.5773 |  | PLAN | 2019-10-25 13:51 | 43763.5773 |  | HVAC&R | CM |  |  | 03:00 | 03:00 | 00:00 | 03:00
288248 | Install water meters water zones JMS B56/26 DWA, B28, TW1,2,3 |  |  |  | 2019-11-01 13:45 | 43770.5726 |  | APPR | 2019-11-01 13:55 | 43770.5796 | NOYESB | BAS | RM |  |  | 00:00 | 18:00 | 14:00 | 04:00
288519 | Prep CP work: Coil Replacement, B12 & B33 [Add CAP# when Pepped] |  | 33-1065 | 3 | 2019-11-06 14:23 | 43775.5994 |  | APPR | 2019-11-06 14:26 | 43775.6012 | WAC | BAS | CP |  |  | 00:00 | 00:00 | 68:00 | -68:00
288876 | B57 BOILER 1,2,3,4 MAINT. 90 day check |  | 57-B200 | 4 | 2019-11-11 04:02 | 43780.1682 |  | APPR | 2020-02-14 13:27 | 43875.5607 | MCCUER | HVAC&R | PM |  |  | 02:00 | 02:00 | 00:00 | 02:00
288964 | [CP] B22 Scientific Air Compressor Replacement (PEP 19-55) |  | 22-1040 | 4 | 2019-11-11 08:24 | 43780.3499 |  | INPRG | 2020-03-05 12:00 | 43895.5002 | WAC | BAS | CP |  |  | 50:00 | 112:00 | 205:45 | -93:45
289005 | B26 Mach Rm Pit Sump Pump Control Panal Auto issue & JCI Alarm |  | 26-1261 | 3 | 2019-11-13 05:22 | 43782.2234 |  | APPR | 2019-11-13 08:34 | 43782.3572 | NOYESB | BAS | CM |  |  | 02:00 | 19:00 | 09:00 | 10:00
FS0019900 | 53-2556...Request to turn up the heat in lab spaces. |  | 53-2556.6 | 4 | 2019-11-13 15:56 | 43782.6642 |  | APPR | 2019-11-13 15:57 | 43782.6649 | WAC | BAS | RM |  |  | 01:00 | 01:00 | 00:00 | 01:00
289057 | [CP] MP24...Engineering Reno MECH Support: Surgical suite move (PEP 19-07) |  | 15-1060 | 4 | 2019-11-15 12:17 | 43784.5116 |  | APPR | 2019-11-15 12:18 | 43784.5122 |  | MECH | CP |  |  | 80:00 | 80:00 | 20:30 | 59:30
289070 | Metasys all items standardization |  | JAXLABS | 5 | 2019-11-16 13:11 | 43785.549 |  | INPRG | 2019-11-16 13:13 | 43785.5506 | NOYESB | BAS | RM |  |  | 160:00 | 160:00 | 11:30 | 148:30
289437 | [CP] B50 GRB Phoenix Valve Upgrades Phs III PEP 20-29 |  | JAXLABS | 4 | 2019-11-18 09:52 | 43787.4109 |  | INPRG | 2020-06-05 10:25 | 43987.4341 | MARTIK | BAS | CP |  |  | 200:00 | 00:00 | 194:30 | -194:30
289444 | [CP] BHB JAX Card Access Upgrades PEP 20-20 [INDEF DEFERR] |  | JAXLABS | 4 | 2019-11-18 11:30 | 43787.4794 |  | HOLD | 2020-04-20 12:54 | 43941.5372 |  | BAS | CP |  |  | 120:00 | 00:00 | 139:30 | -139:30
289447 | [CP-2020] B50 Hot Water System Replacement PEP 20-03 |  | JAXLABS | 4 | 2019-11-18 11:38 | 43787.485 |  | APPR | 2020-01-28 15:05 | 43858.6288 |  | MECH | CP |  |  | 80:00 | 120:00 | 25:00 | 95:00
289449 | [CP-2020] B12 AHU 1&2 Reclaim Coils PEP 20-05 |  | JAXLABS | 4 | 2019-11-18 11:41 | 43787.4866 |  | APPR | 2020-03-30 07:17 | 43920.3032 |  | HVAC&R | CP |  |  | 120:00 | 120:00 | 13:00 | 107:00
289453 | [CP-2020] B28/50 ETC Autoclave Controls PEP 20-35 |  | JAXLABS | 4 | 2019-11-18 11:45 | 43787.4898 |  | APPR | 2020-01-16 14:20 | 43846.5974 |  | MECH | CP |  |  | 40:00 | 00:00 | 244:30 | -244:30
289454 | [CP] B28 Bottle Machine #1 Overhaul PEP 20-36 [IND DEFERRED] |  | 28 | 4 | 2019-11-18 11:47 | 43787.4909 |  | HOLD | 2020-04-20 07:52 | 43941.3277 |  | MECH | CP |  |  | 200:00 | 00:00 | 01:00 | -01:00
289459 | [CP-2020] B28 Domestic Hot Water System PEP 20-09 |  | 28-1 | 4 | 2019-11-18 11:53 | 43787.4953 |  | APPR | 2020-02-11 15:14 | 43872.6346 |  | MECH | CP |  |  | 120:00 | 120:00 | 87:30 | 32:30
289470 | [CP] BHB JCI Control Upgrades PEP 20-17 [IND DEFERRED] |  | JAXLABS | 4 | 2019-11-18 13:20 | 43787.5557 |  | APPR | 2020-05-13 07:44 | 43964.3222 | WAC | BAS | CP |  |  | 40:00 | 00:00 | 74:30 | -74:30
289552 | [CP] B310 JW HVAC Controls Upgrade and Commissioning PEP 19-47 |  | JAXWEST | 4 | 2019-11-21 08:24 | 43790.35 |  | INPRG | 2019-11-21 08:26 | 43790.3515 | MARTIK | BAS | CP |  |  | 400:00 | 2200:00 | 2056:30 | 143:30
289795 | B21 Supply cabinet Motor #4 Bearing change or new motor/on hold |  | 21-5010 | 4 | 2019-11-27 12:55 | 43796.5381 |  | HOLD | 2020-06-17 15:08 | 43999.6308 | PELLES | HVAC&R | CM |  |  | 06:00 | 00:00 | 14:30 | -14:30
290087 | SM - B50 Chilled Water pumps 3&4/Order pump parts/check vsd bypass spring |  | 50-B101 | 4 | 2019-12-04 09:04 | 43803.378 |  | APPR | 2020-06-19 14:54 | 44001.6209 | PELLES | HVAC&R | CM |  |  | 08:00 | 20:00 | 02:30 | 17:30
290193 | SWO - VAT WORK FOR BH UTILITY PLANT (ANNUAL, 2020) |  | JAXLABS | 3 | 2019-12-09 04:01 | 43808.1671 |  | APPR | 2019-12-09 04:01 | 43808.1671 |  | HVAC&R | PM |  |  | 00:00 | 00:00 | 82:00 | -82:00
290306 | SWO - BAS R&D (BH) (ANNUAL, 2020) |  | JAXLABS | 5 | 2019-12-09 04:02 | 43808.1677 |  | APPR | 2020-01-03 07:49 | 43833.3259 |  | BAS | CM |  |  | 00:00 | 00:00 | 04:00 | -04:00
290419 | B33 EF-6 vibrating in 2165 lab. Upgrade honeywell controls for misc fans basement |  | 33-2165 | 3 | 2019-12-10 09:06 | 43809.3792 |  | APPR | 2020-04-28 09:27 | 43949.3938 | PELLES | HVAC&R | CM |  |  | 32:00 | 19:00 | 00:00 | 19:00
290582 | Review with Chris K. all Process Equipment SOP's |  | JAXLABS | 4 | 2019-12-16 13:25 | 43815.559 |  | APPR | 2019-12-16 13:33 | 43815.5646 | PBARBEAU | MECH | RM |  |  | 00:00 | 05:00 | 19:00 | -14:00
290596 | B28 Rm# 2205 Perimeter heat/order & replace valve |  | 28-2205 | 4 | 2019-12-17 10:20 | 43816.4305 |  | APPR | 2020-01-07 07:19 | 43837.3049 | PELLES | HVAC&R | CM |  |  | 04:00 | 08:00 | 00:00 | 08:00
290630 | B35 BOILER 1 2 & 3 add clear pvc holders on drains(one broken) |  | 35-B045 | 4 | 2019-12-18 13:15 | 43817.5523 |  | APPR | 2020-01-14 07:47 | 43844.324 | MCCUER | HVAC&R | CM |  |  | 04:00 | 04:00 | 00:00 | 04:00
290631 | Activate B50 oxygen gas manifold alarm Per Greg Hiltz request once SOP referenced |  | 50 | 4 | 2019-12-18 13:30 | 43817.5622 |  | APPR | 2019-12-18 13:41 | 43817.5699 | NOYESB | BAS | RM |  |  | 00:00 | 04:00 | 02:30 | 01:30
291172 | BAS Eval...NRB sliding doors impact air balancing in labs/hallways |  | 33-2000 | 4 | 2020-01-02 09:22 | 43832.39 |  | APPR | 2020-01-02 09:26 | 43832.3928 | WAC | BAS | CM |  |  | 08:00 | 16:00 | 00:00 | 16:00
291488 | SWO - VAT WORK, JMS (BH-ANNUAL SWO, 2020) |  | JAXLABS | 3 | 2020-01-06 04:02 | 43836.1683 |  | APPR | 2020-01-06 04:02 | 43836.1683 |  | HVAC&R | PM |  |  | 00:00 | 00:00 | 32:30 | -32:30
291489 | SWO - VAT WORK, RL (BH-ANNUAL SWO, 2020) |  | JAXLABS | 3 | 2020-01-06 04:02 | 43836.1683 |  | APPR | 2020-01-06 04:02 | 43836.1683 |  | HVAC&R | PM |  |  | 00:00 | 00:00 | 40:00 | -40:00
291953 | [CP] B29,30,31,32 Replace humidifiers PEP 20-25 [IND DEFERRED] |  | 29-1115 | 4 | 2020-01-15 08:17 | 43845.3453 |  | HOLD | 2020-04-20 07:49 | 43941.3254 | WAC | BAS | CP |  |  | 00:00 | 00:00 | 04:00 | -04:00
291975 | B31 AX 09 Room humidifier overshooting |  | 31 | 4 | 2020-01-16 14:25 | 43846.6005 |  | INPRG | 2020-01-16 14:27 | 43846.6019 | NOYESB | BAS | CM |  |  | 06:00 | 06:00 | 24:30 | -18:30
291996 | [CP] Trailer 22/23 Engineering CP project (PEP 19-51) |  | MOD | 3 | 2020-01-17 16:10 | 43847.6734 |  | APPR | 2020-01-17 16:12 | 43847.6752 | WAC | BAS | CP |  |  | 100:00 | 100:00 | 09:00 | 91:00
291999 | B01A Unit 1 AHU-123 Replacement (PEP 19-56) |  | 20-4355A | 3 | 2020-01-17 16:19 | 43847.6799 |  | APPR | 2020-01-17 16:21 | 43847.6815 | WAC | BAS | CP |  |  | 100:00 | 40:00 | 53:30 | -13:30
292000 | B32 Flow problems |  | 32-1115 | 5 | 2020-01-17 18:43 | 43847.7798 |  | INPRG | 2020-01-17 18:44 | 43847.7809 | NOYESB | BAS | CM |  |  | 10:00 | 00:00 | 04:30 | -04:30
292171 | B62 receiving room too cold/ Ice covering propane heater intake |  | 62-1200 | 3 | 2020-01-21 13:46 | 43851.5737 |  | APPR | 2020-01-21 15:12 | 43851.6334 | MCCUER | HVAC&R | CM |  |  | 03:00 | 00:00 | 05:00 | -05:00
FS0022122 | 50-1160...-80 freezer is not holding temperature [EVAL] |  | 50-1160 | 4 | 2020-01-30 09:28 | 43860.3947 |  | APPR | 2020-04-09 15:46 | 43930.6566 | MCCUER | HVAC&R | CM |  |  | 01:00 | 01:30 | 28:30 | -27:00
292910 | B03 Air Compressor: Re-pipe posidrain & regulatobalson filter(schedule time to shutoff bowls (order) |  | 03-1080 | 4 | 2020-02-04 16:19 | 43865.6802 |  | APPR | 2020-06-01 17:51 | 43983.7435 | HWL | HVAC&R | CM |  |  | 04:00 | 04:00 | 05:30 | -01:30
292933 | Bldg=-31 AHU is not going into Face & By pass mode for heating |  | 31-1115 | 2 | 2020-02-06 01:20 | 43867.0554 |  | APPR | 2020-02-06 06:45 | 43867.2815 | NOYESB | BAS | CM |  |  | 01:00 | 06:00 | 15:00 | -09:00
293265 | B59 BOILERS 1,2,3 - 90-DAY MAINT. CHECKS/ANNUAL CLEANING |  | 59-B010 | 4 | 2020-02-10 04:02 | 43871.1682 |  | APPR | 2020-02-21 14:46 | 43882.615 | MCCUER | HVAC&R | PM |  |  | 02:00 | 02:00 | 00:00 | 02:00
293360 | Clean & protect CO2 copper line Acid room B28 |  | 28-1 | 4 | 2020-02-10 12:38 | 43871.5263 |  | APPR | 2020-02-10 12:47 | 43871.5329 | PBARBEAU | MECH | RM |  |  | 02:00 | 02:00 | 02:00 | 00:00
293374 | Water Usage B26,56 & 32 trouble shoot water usage |  | 26 | 3 | 2020-02-10 14:47 | 43871.6157 |  | INPRG | 2020-02-27 12:48 | 43888.533 | WEAVEC | MECH | CM |  |  | 00:00 | 00:00 | 32:00 | -32:00
293548 | JMS AHU MEDIA CHECKS |  | JAXLABS | 4 | 2020-02-17 04:01 | 43878.1674 |  | APPR | 2020-03-26 15:33 | 43916.6482 | GRW | HVAC&R | PM |  |  | 04:00 | 04:00 | 24:30 | -20:30
294174 | B29,30,31,32 Change AHU sheaves/B-belt experiment |  | 29-1115 | 3 | 2020-02-24 12:36 | 43885.5247 |  | APPR | 2020-03-30 09:46 | 43920.4072 | PELLES | HVAC&R | CM |  |  | 24:00 | 24:00 | 28:00 | -04:00
294221 | B33-1080: Re-program Revco farm for pressure control |  | 33-1080 | 4 | 2020-02-27 07:54 | 43888.3293 |  | APPR | 2020-02-27 08:28 | 43888.3526 | NOYESB | BAS | CM |  |  | 16:00 | 16:00 | 03:00 | 13:00
294224 | B53-G125/128: Update fan logic |  | 53-G125 | 4 | 2020-02-27 12:50 | 43888.5349 |  | APPR | 2020-02-27 14:09 | 43888.5898 | NOYESB | BAS | CM |  |  | 50:00 | 50:00 | 06:00 | 44:00
294483 | [CP] B33 NRB Preheat Coil Replacement PEP 20-28 |  | 33-1065 | 4 | 2020-03-05 09:23 | 43895.3912 |  | INPRG | 2020-06-17 14:57 | 43999.6232 | WAC | BAS | CP |  |  | 60:00 | 180:00 | 136:00 | 44:00
294519 | BLDG 12 JMS MODULAR 22,23,24 EF WORK |  | 12 | 3 | 2020-03-09 04:00 | 43899.1668 |  | APPR | 2020-06-19 07:33 | 44001.3142 | HWL | HVAC&R | PM |  |  | 03:00 | 12:00 | 06:00 | 06:00
294933 | 01E-2235...Damper motor isn't working - needs to be changed before cooling season |  | 01E-2235 | 3 | 2020-03-09 12:42 | 43899.5294 |  | APPR | 2020-04-02 15:17 | 43923.6369 | NOYESB | BAS | CM |  |  | 08:00 | 00:00 | 27:00 | -27:00
295220 | Offline Devices |  | JAXLABS | 4 | 2020-03-20 09:44 | 43910.4052 |  | INPRG | 2020-03-20 15:06 | 43910.6293 | MARTIK | BAS | CM |  |  | 80:00 | 80:00 | 68:30 | 11:30
295459 | MP15...Thermostat in dirty & clean airlocks is hanging off the wall, outside cover is broke |  | 12-1150 | 3 | 2020-03-24 09:11 | 43914.3823 |  | APPR | 2020-07-14 14:57 | 44026.6232 | NOYESB | BAS | CM |  |  | 01:00 | 02:00 | 04:00 | -02:00
295619 | B21 BRL 1ST 2ND, 3RD & 4TH EXHAUST CHECK |  | 21 | 4 | 2020-03-30 04:01 | 43920.1673 |  | APPR | 2020-06-16 14:49 | 43998.6177 |  | HVAC&R | PM |  |  | 04:00 | 04:00 | 04:30 | -00:30
FS0023534 | 28-1070...Separate roller/shavings dispenser controls, TW2 & 3 (see long desc) |  | 28-1070 | 3 | 2020-04-02 15:47 | 43923.6573 |  | APPR | 2020-04-30 13:21 | 43951.5563 | BOB | BAS | RM |  |  | 02:00 | 03:00 | 00:00 | 03:00
295822 | Ultra Loq Failure Slot 27 NRB Farm Response & Repair |  | 33 | 2 | 2020-04-03 14:37 | 43924.6092 |  | APPR | 2020-04-03 14:43 | 43924.6129 | MCCUER | HVAC&R | CM |  |  | 08:00 | 08:00 | 00:00 | 08:00
295894 | [CP] B17 Chiller #6 and #7 Replacement PEP18-160-BAS Support |  | 17-1010 | 4 | 2020-04-09 15:22 | 43930.6401 |  | INPRG | 2020-04-09 15:25 | 43930.6422 | MARTIK | BAS | CP |  |  | 24:00 | 40:00 | 60:00 | -20:00
296445 | RAF CHILLED WATER STRAINERS & VENTS 365 DAY MAINT. |  | JAXLABS | 3 | 2020-04-20 04:00 | 43941.1668 |  | APPR | 2020-05-11 10:58 | 43962.4567 | HWL | HVAC&R | PM |  |  | 09:00 | 15:00 | 21:00 | -06:00
296452 | RAF ULTRA LOW FREEZERS 90 DAY MAINTENANCE |  | JAXLABS | 4 | 2020-04-20 04:00 | 43941.1668 |  | APPR | 2020-07-02 14:48 | 44014.6167 | GRW | HVAC&R | PM |  |  | 16:00 | 16:00 | 00:00 | 16:00
296495 | BLDG 01 RAF(INSIDE)AHU-EF PM WORK(123AHU, AHU14 & MISC AHU/EF)123 pm done |  | 01 | 3 | 2020-04-20 04:01 | 43941.167 |  | APPR | 2020-06-19 13:47 | 44001.5745 | HWL | HVAC&R | PM |  |  | 06:00 | 18:00 | 12:00 | 06:00
296499 | BLDG 01 RAF(outside/roof) AHU-EF PM WORK(Rooftop ahus &CSA/WA ahu/ef) |  | 01D-ROOF | 3 | 2020-04-20 04:01 | 43941.1671 |  | APPR | 2020-06-19 07:43 | 44001.3219 | HWL | HVAC&R | PM |  |  | 06:00 | 18:00 | 22:30 | -04:30
296503 | RAF AHU MEDIA CHECKS |  | 01 | 4 | 2020-04-20 04:01 | 43941.1671 |  | APPR | 2020-05-01 15:18 | 43952.6373 | GRW | HVAC&R | PM |  |  | 04:00 | 04:00 | 31:00 | -27:00
296662 | Install VAT sensors in newly installed CT-16 |  | 17-GRND | 3 | 2020-04-20 12:40 | 43941.5279 |  | APPR | 2020-04-21 08:59 | 43942.3746 | PELLES | HVAC&R | CM |  |  | 04:00 | 04:00 | 00:00 | 04:00
296835 | Remove Oil & Refrigerant from old Refrigerant equipment May-Oct 2020 |  | JAXLABS | 4 | 2020-04-23 10:31 | 43944.4382 |  | APPR | 2020-04-23 10:33 | 43944.4394 | PELLES | HVAC&R | CM |  |  | 08:00 | 30:00 | 07:30 | 22:30
296902 | BLDG 12 JMS AHU-EF PM WORK |  | 12-2080 | 3 | 2020-04-27 04:00 | 43948.1669 |  | APPR | 2020-06-19 07:41 | 44001.3204 | HWL | HVAC&R | PM |  |  | 03:00 | 21:00 | 19:30 | 01:30
FS0041608 | 28-1060...Some of the air handler ducts in the rear of WSA are totally rotted out. |  | 28-1060 | 3 | 2020-04-28 12:26 | 43949.5178 |  | APPR | 2020-05-19 09:22 | 43970.3905 | WAC | BAS | CM |  |  | 01:00 | 00:00 | 00:00 | 00:00
FS0042664 | 59-3...Evaluate air handling system - B59 3rd floor. See long description. |  | 59-3 | 3 | 2020-05-04 13:02 | 43955.5434 |  | APPR | 2020-05-05 08:05 | 43956.3368 | WAC | BAS | CM |  |  | 02:00 | 30:00 | 12:30 | 17:30
297460 | NRB Basement...Clean refrigeration repair shop |  | 33 | 5 | 2020-05-05 12:54 | 43956.5372 |  | APPR | 2020-05-05 12:54 | 43956.5376 | MCCUER | HVAC&R | NC |  |  | 08:00 | 08:00 | 06:30 | 01:30
297462 | Weigh old refrigerant tanks, get pricing on exchange |  | 33 | 5 | 2020-05-05 12:57 | 43956.5394 |  | APPR | 2020-05-05 12:58 | 43956.5405 | MCCUER | HVAC&R | CM |  |  | 05:00 | 05:00 | 08:00 | -03:00
297506 | BLDG 26,32,56 JMS AHU-EF PM WORK(schedule B56 ssa ef) |  | 32 | 3 | 2020-05-11 04:00 | 43962.1668 |  | APPR | 2020-07-14 15:09 | 44026.6315 | HWL | HVAC&R | PM |  |  | 12:00 | 24:00 | 00:00 | 24:00
297913 | Building 50 Sand Filters Going Offline |  | 50-3202 | 3 | 2020-05-13 08:23 | 43964.3496 |  | INPRG | 2020-05-14 14:45 | 43965.6143 | WEAVEC | MECH | CM |  |  | 04:00 | 14:00 | 22:30 | -08:30
FS0045571 | AX3...PIV rack blast gate issues (see long description) |  | 15-1030 | 3 | 2020-05-15 10:50 | 43966.4514 |  | APPR | 2020-05-18 11:16 | 43969.4696 | WAC | BAS | CM |  |  | 02:00 | 02:00 | 05:00 | -03:00
297971 | BLDG 51 JMS AHU-EF PM WORK |  | 12-2000 | 3 | 2020-05-18 04:00 | 43969.1668 |  | APPR | 2020-06-19 14:27 | 44001.6021 | HWL | HVAC&R | PM |  |  | 32:00 | 32:00 | 25:00 | 07:00
297988 | RAF EMERGENCY/EXIT LIGHTING INSPECTIONS |  | JAXLABS | 3 | 2020-05-18 04:00 | 43969.1669 |  | APPR | 2020-05-19 10:21 | 43970.4314 |  | MECH | PM |  |  | 25:00 | 50:00 | 18:30 | 31:30
298100 | RAF DWA - PRESSURE WASH DRAINS |  | 01B-1650 | 3 | 2020-05-18 04:01 | 43969.1675 |  | PLAN | 2020-05-18 04:01 | 43969.1675 |  | MECH |  |  |  | 02:00 | 04:00 | 00:00 | 04:00
FS0045809 | 28-1070...Box #3 dryer not keeping temp; ranging from 194-218 |  | 28-1070 | 2 | 2020-05-18 10:57 | 43969.4565 |  | APPR | 2020-05-18 10:59 | 43969.4577 | WEAVEC | MECH | CM |  |  | 02:00 | 00:00 | 02:00 | -02:00
298325 | Oasis Cafe...Install ice/water dispenser [Multiple trades needed] |  | 55-2503 | 4 | 2020-05-19 07:36 | 43970.3166 |  | APPR | 2020-05-27 14:54 | 43978.6206 |  | MECH | CM |  |  | 04:00 | 27:00 | 08:30 | 18:30
298346 | Tech air Box senser needs cleaning reporting High Alarm |  | 53-1448 | 3 | 2020-05-20 14:54 | 43971.6206 |  | APPR | 2020-05-20 14:57 | 43971.6226 | MCCUER | HVAC&R | CM |  |  | 02:00 | 03:00 | 06:00 | -03:00
298374 | BAS/HVAC COVID-Related Planning & Modifications |  | JAXLABS | 3 | 2020-05-22 08:14 | 43973.343 |  | APPR | 2020-05-22 08:16 | 43973.3446 | BOB | BAS | CM |  |  | 40:00 | 40:00 | 15:30 | 24:30
FS0048226 | 21-2295...Lab is too hot. Please adjust temperature. |  | 21-2295 | 3 | 2020-05-29 10:13 | 43980.4254 |  | APPR | 2020-05-29 10:13 | 43980.426 | WAC | BAS | CM |  |  | 01:00 | 01:00 | 00:00 | 01:00
298705 | Replace AHU 7 intake duct B28 Mech room |  | 28-2050 | 3 | 2020-05-29 15:32 | 43980.6471 |  | APPR | 2020-05-29 15:35 | 43980.6494 | WAC | BAS | CM |  |  | 20:00 | 20:00 | 11:00 | 09:00
298878 | PE - JMS WASH EQUIPMENT ODD-MONTH OPER/INSP PM |  |  | 3 | 2020-06-01 04:01 | 43983.1677 |  | APPR | 2020-07-11 07:57 | 44023.3314 |  | MECH | PM |  |  | 25:00 | 44:00 | 02:00 | 42:00
298881 | SWO - MECH RL (JULY) |  | JAXLABS | 3 | 2020-06-01 04:01 | 43983.1677 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | MECH | CM |  |  | 00:00 | 00:00 | 04:00 | -04:00
298882 | SWO - MECH JMS (JULY) |  | JAXLABS | 3 | 2020-06-01 04:01 | 43983.1677 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | MECH | CM |  |  | 00:00 | 00:00 | 06:00 | -06:00
298885 | SWO - HVAC JMS (JULY) |  | JAXLABS | 3 | 2020-06-01 04:02 | 43983.1677 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | HVAC&R | CM |  |  | 00:00 | 00:00 | 01:00 | -01:00
298961 | B06 AHU-D1 add auto lubers and look at drain pan |  | 06-1200 | 3 | 2020-06-01 07:37 | 43983.3174 |  | APPR | 2020-06-19 13:24 | 44001.5583 | HWL | HVAC&R | CM |  |  | 03:00 | 03:00 | 08:30 | -05:30
299013 | B20 ARL AHU 1A order 2 different fan bearings & fan wheel. |  | 19-4355D | 3 | 2020-06-03 14:23 | 43985.599 |  | APPR | 2020-06-03 14:31 | 43985.605 | HWL | HVAC&R | CM |  |  | 04:00 | 04:00 | 00:00 | 04:00
299077 | BLDG 29,30,31 JMS AHU-EF PM WORK |  | 29-1115 | 3 | 2020-06-08 04:00 | 43990.1668 |  | APPR | 2020-06-19 14:36 | 44001.6081 | HWL | HVAC&R | PM |  |  | 12:00 | 18:00 | 00:00 | 18:00
299129 | SWO - PREP FREEZERS/FRIDGES FOR DISPOSAL (JULY) |  | 33 | 4 | 2020-06-08 04:01 | 43990.1672 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | HVAC&R | CM |  |  | 08:00 | 08:00 | 00:00 | 08:00
299344 | PE - JMS AUTOCLAVE/STERILIZER MONTHLY PM |  |  | 3 | 2020-06-08 04:02 | 43990.1682 |  | APPR | 2020-06-08 14:23 | 43990.5991 |  | MECH | PM |  |  | 25:00 | 44:00 | 05:00 | 39:00
299354 | SWO - BAS ALARM MANAGEMENT JMS (JULY) |  | JAXLABS | 3 | 2020-06-08 04:02 | 43990.1683 |  | INPRG | 2020-07-08 07:45 | 44020.3229 | MARTIK | BAS | CM |  |  | 36:00 | 00:00 | 02:00 | -02:00
299355 | SWO - HVAC RAF (JULY) |  | JAXLABS | 3 | 2020-06-08 04:02 | 43990.1683 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | HVAC&R | CM |  |  | 00:00 | 00:00 | 01:30 | -01:30
299358 | SWO - BAS RL (JULY) |  | JAXLABS | 3 | 2020-06-08 04:02 | 43990.1683 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | BAS | CM |  |  | 00:00 | 00:00 | 03:00 | -03:00
299359 | SWO - BAS ALARM MANAGEMENT RL (JULY) |  | JAXLABS | 3 | 2020-06-08 04:02 | 43990.1683 |  | INPRG | 2020-07-08 07:45 | 44020.3232 | MARTIK | BAS | CM |  |  | 00:00 | 00:00 | 04:00 | -04:00
299360 | SWO - BAS JMS (JULY) |  | JAXLABS | 3 | 2020-06-08 04:02 | 43990.1683 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | BAS | CM |  |  | 00:00 | 00:00 | 03:00 | -03:00
299364 | SWO - DAILY HVAC SPACE CHECKS - JMS (JULY) |  | JAXLABS | 3 | 2020-06-08 04:02 | 43990.1683 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | HVAC&R | PM |  |  | 00:00 | 00:00 | 01:30 | -01:30
299365 | SWO - DAILY HVAC SPACE CHECKS - RL (JULY) |  | JAXLABS | 3 | 2020-06-08 04:02 | 43990.1683 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | HVAC&R | PM |  |  | 00:00 | 00:00 | 09:30 | -09:30
299367 | SWO - STRAPPING MACHINE REPAIRS (JULY) |  | 28-1 | 3 | 2020-06-08 04:02 | 43990.1683 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | MECH | CM |  |  | 00:00 | 00:00 | 02:00 | -02:00
299535 | High Seas - Move evaporator |  | 35-1050 | 4 | 2020-06-14 22:50 | 43996.9514 |  | INPRG | 2020-06-14 22:51 | 43996.9519 | MCCUER | HVAC&R | CM |  |  | 10:00 | 10:00 | 39:00 | -29:00
299614 | SWO - QUARTERLY EYEWASH & EYE SHOWER PRESSURE ADJ.(JULY-SEPT) |  | JAXLABS | 3 | 2020-06-15 04:01 | 43997.1672 |  | APPR | 2020-07-06 09:27 | 44018.3937 |  | MECH | CM |  |  | 40:00 | 40:00 | 00:00 | 40:00
299736 | VAT sensor installation B29-32 Bottom units/fan bearings |  | 29-1115 | 4 | 2020-06-17 07:17 | 43999.3035 |  | APPR | 2020-06-29 15:15 | 44011.6352 | PELLES | HVAC&R | CM |  |  | 10:00 | 10:00 | 05:00 | 05:00
299749 | JMS CHILLED WATER STRAINERS & VENTS 365 DAY MAINT. |  | JAXLABS | 3 | 2020-06-17 15:25 | 43999.6424 |  | APPR | 2020-06-17 15:27 | 43999.644 | GRW | HVAC&R | PM |  |  | 14:00 | 00:00 | 07:00 | -07:00
299767 | B74 Catwalk install support |  | 74-P005 | 3 | 2020-06-18 07:52 | 44000.328 |  | APPR | 2020-06-18 07:55 | 44000.33 | WAC | BAS | CM |  |  | 08:00 | 08:00 | 05:00 | 03:00
299782 | Calender Cottage heat pump drain pan leak |  | 44A | 5 | 2020-06-18 15:18 | 44000.6373 |  | APPR | 2020-06-19 08:44 | 44001.3641 | NOYESB | BAS | RM |  |  | 01:00 | 01:00 | 01:00 | 00:00
299783 | Chilled Water/Reclaim Systems-Seasonal Functional Check |  | JAXLABS | 4 | 2020-06-18 15:20 | 44000.6392 |  | APPR | 2020-06-18 15:22 | 44000.6402 | NOYESB | BAS | PM |  |  | 00:00 | 04:00 | 09:00 | -05:00
FS0052430 | G3B...Whooshing sound coming from vents. |  | 50-3140 | 3 | 2020-06-19 10:19 | 44001.4301 |  | APPR | 2020-06-19 10:20 | 44001.4308 | WAC | BAS | CM |  |  | 02:00 | 08:00 | 02:00 | 06:00
300062 | B22 & B65 Rotary Air Comp Service & B74 service |  | 22-1000 | 3 | 2020-06-25 07:28 | 44007.3111 |  | APPR | 2020-06-25 07:29 | 44007.3118 | HWL | HVAC&R | PM |  |  | 02:00 | 04:00 | 07:00 | -03:00
300238 | SWO - MECH RL (AUG) |  | JAXLABS | 3 | 2020-06-29 04:01 | 44011.1676 |  | APPR | 2020-07-07 15:29 | 44019.6452 |  | MECH | CM |  |  | 00:00 | 00:00 | 06:00 | -06:00
300392 | B53 G107 hood damper |  | 53-G107 |  | 2020-07-01 15:09 | 44013.631 |  | APPR | 2020-07-01 15:09 | 44013.6316 | NOYESB | BAS | CM |  |  | 00:00 | 02:00 | 02:30 | -00:30
300452 | BLDG 55 RAF AHU-EF PM WORK 8/5 |  | 55 | 3 | 2020-07-06 04:00 | 44018.167 |  | APPR | 2020-07-14 15:19 | 44026.638 | HWL | HVAC&R | PM |  |  | 05:00 | 25:00 | 00:00 | 25:00
300750 | crac unit # 3 compressor replace - couldnt find WO |  | 59-1100 | 3 | 2020-07-06 07:15 | 44018.3021 |  | APPR | 2020-07-06 07:16 | 44018.3027 | MCCUER | HVAC&R | CM |  |  | 08:00 | 00:00 | 08:00 | -08:00
FS0056286 | 28-1050...Tunnel #2 & 3 need wash pump screen bolts replaced. All are stripped. |  | 28-1050B | 3 | 2020-07-07 15:08 | 44019.6307 |  | APPR | 2020-07-07 15:28 | 44019.6443 | PBARBEAU | MECH | CM |  |  | 01:00 | 00:00 | 01:00 | -01:00
300823 | MGL-375...Room temp is reading 73.6 degrees - please lower temp (70 degrees) |  | 19-3630 | 3 | 2020-07-09 09:19 | 44021.3878 |  | APPR | 2020-07-09 09:21 | 44021.3894 | MARTIK | BAS | CM |  |  | 01:00 | 01:00 | 02:00 | -01:00
FS0056741 | 20-3835...Wall vent near section 28 is very loud, louder than the other vents in the room. |  | 20-3835 | 3 | 2020-07-09 09:43 | 44021.4047 |  | APPR | 2020-07-09 09:47 | 44021.4078 | NOYESB | BAS | CM |  |  | 02:00 | 04:00 | 02:00 | 02:00
300837 | Annex 3 high humidity"s PIV exhaust |  | 15-1030 | 2 | 2020-07-10 09:18 | 44022.3874 |  | APPR | 2020-07-10 09:38 | 44022.4014 | DPG | HVAC&R | EM |  |  | 00:00 | 00:00 | 01:00 | -01:00
FS0057050 | 33-3165..."Beer cooler" is running warm, holding at 10C, from 4C. |  | 33-3165 | 3 | 2020-07-10 13:24 | 44022.5581 |  | APPR | 2020-07-13 08:43 | 44025.3632 | GRW | HVAC&R | CM |  |  | 01:00 | 01:00 | 02:00 | -01:00
301078 | B55 EF-3 & 4 Severe misalignment imbalance-VAT |  | 55-3992 | 3 | 2020-07-13 11:01 | 44025.4588 |  | APPR | 2020-07-14 15:37 | 44026.6505 | PELLES | HVAC&R | CM |  |  | 04:00 | 00:00 | 00:00 | 00:00
FS0057295 | 21-1310...Thermo scientific water system is not functioning. Message says "leakage". |  | 21-1310 | 3 | 2020-07-13 14:42 | 44025.6128 |  | APPR | 2020-07-15 15:00 | 44027.6249 | PBARBEAU | MECH | CM |  |  | 01:00 | 00:00 | 02:00 | -02:00
FS0057399 | 57-1915...Roscoe's Dish machine not draining properly |  | 57-1915 | 4 | 2020-07-13 15:25 | 44025.6421 |  | APPR | 2020-07-14 13:53 | 44026.5784 | WEAVEC | MECH | RM |  |  | 02:00 | 03:00 | 00:00 | 03:00
301093 | B33 3rd Floor Water Fountain Leak |  | 33-3010 | 3 | 2020-07-13 23:31 | 44025.9799 |  | INPRG | 2020-07-14 08:13 | 44026.3421 | GRW | HVAC&R | CM |  |  | 03:00 | 02:00 | 02:30 | -00:30
FS0057660 | 33-2060...Ice maker in shared equipment room has been tripping the internal breaker. |  | 33-2060 | 4 | 2020-07-14 12:24 | 44026.5165 |  | APPR | 2020-07-14 15:29 | 44026.6453 | GRW | HVAC&R | CM |  |  | 01:00 | 01:00 | 00:30 | 00:30
301106 | 28-1060...Sterilizer 5 low temp alarm again 7/14 |  | 28-1060 | 3 | 2020-07-14 13:08 | 44026.5472 |  | APPR | 2020-07-14 13:09 | 44026.5478 | PBARBEAU | MECH | CM |  |  | 02:00 | 06:00 | 00:00 | 06:00
FS0057400 | MP22...Key card reader is not reading the cards |  | MOD-1230 | 3 | 2020-07-14 14:16 | 44026.5943 |  | APPR | 2020-07-15 09:13 | 44027.3837 | MARTIK | BAS | CM |  |  | 02:00 | 02:00 | 00:00 | 02:00
FS0057232 | 55-2nd & 3rd floors - Unusual, loud humming sound. Constant sound heard on 2nd & 3rd floors. |  | 55-2 | 3 | 2020-07-14 14:18 | 44026.5959 |  | APPR | 2020-07-14 14:55 | 44026.6218 | NOYESB | BAS | CM |  |  | 02:00 | 04:00 | 00:00 | 04:00
FS0025156 | 33-3150...Nanopure water system was repaired this week, but is now going into "self test" mode while |  | 33-3150 | 3 | 2020-07-15 07:31 | 44027.3132 |  | APPR | 2020-07-15 09:23 | 44027.3913 | DORITS | MECH | CM |  |  | 01:00 | 02:00 | 02:00 | 00:00
FS0057998 | AX28...Stage 1 dressing room floor sink leaks slowly. |  | 51-1630 | 3 | 2020-07-15 13:36 | 44027.5666 |  | APPR | 2020-07-15 14:22 | 44027.5987 | WEAVEC | MECH | CM |  |  | 01:00 | 00:00 | 00:00 | 00:00
301130 | b28 machine room standing water |  | 28-1060 | 3 | 2020-07-16 05:30 | 44028.2295 |  | PLAN | 2020-07-16 05:30 | 44028.2295 | PBARBEAU | MECH | CM |  |  | 00:00 | 00:00 | 00:00 | 00:00
Number of Records: |  | 154
Saved Where Clause: |  | ( ( workorder.woclass = 'WORKORDER' or workorder.woclass = 'ACTIVITY' ) and ( workorder.status = 'HOLD' or workorder.status = 'APPR' or workorder.status = 'INPRG' or workorder.status = 'PLAN' ) and workorder.historyflag = 0 and ( workorder.persongroup = 'MECH' or workorder.persongroup = 'HVAC&R' or workorder.persongroup = 'BAS' ) and workorder.siteid = 'BARHBR' and workorder.istask = 0 )
Run Time Where Clause: |  | ((woclass = 'WORKORDER' or woclass = 'ACTIVITY') and historyflag = 0 and istask = 0 and siteid = 'BARHBR')
7/16/20 7:14 AM | [6 empty] | 1 | [6 empty] | / | 4